## sprint 1
Group: |  |  |  |  | People
|  | Completed in Sprint 1 | Completed in Sprint 2 | In Progress | Lead | Contributed | Notes
1 | 1. 4 Possible Fan Groups |  | X |  | Alex | Jason | There is technically 4 groups, they aren't named however
2 | 1a. Choice of # Groups |  |  | X | Alex |  | Hard coded to 4, not a choice
3 | 2. Display as flexible size grid |  | X |  | Alex | Jason
4 | 3. Display groups via color |  | X |  | Jason
5 | 4. Chose Initial positions randomly | X |  |  | Jason
6 | 5. Vary population density |  | X |  | Alex
7 | 6. World Wrap or Not |  | X |  | Alex
8 | 7. Diagonal neighbors |  | X |  | Alex
9 | 8. Adjustable homogeniety preference |  | X
10 | 9. Different Satisfaction Grains | X |  |  | Tien
11 | 9a. Overall or by Group |  |  | X | Jason
12 | 9b. Random Individual preference | [5 empty] | Not planned
13 | 10. Choices for Movement Alg. | [5 empty] | Not planned
14 | 10a. Move to random empty |  | X |  | Alex
15 | 10b. Move to closest empty | [5 empty] | Not planned
16 | 10c. Move targeted for group | [5 empty] | Not planned
17 | 11. Animation timing |  | X |  | Tien
18 | 12. Single Step or Run |  | X |  | Jason | Alex
19 | 13. Output # Cycles |  | X |  | Tien
20 | 14. Output satisfaction ongoing |  | X |  | Alex
21 | 15. Output same group pct ongoing | [5 empty] | Not planned
22 | 16. Avoid infinite repeat |  | X |  | Tien
23 | 17. User can stop | X |  |  | Tien
24 | 18. Write results to file | [5 empty] | Not planned
25 | 19. Experiment repeat simulation | [5 empty] | Not planned
26 | 20. Show traces | [5 empty] | Not planned